## Slide 1
MXXI
METRIXX / ILLINI
Intern Server Initiative · Powered by UIUC MSFE Quant Team
TEAM KICKOFF · JUNE 3, 2026
JUN 12
DEMO DAY
ILLINI
SERVER
5 INTERNS
TEAM
Jim Marzano · Founder & CEO, Metrixx LLC · CBOT/CME Member · Founding Member GNMA Mortgage Futures · Original Bloomberg Data Contributor

## Slide 2
MXXI — WHAT WE'RE BUILDING
An independent intern server that accelerates Demo Day and cements team authorship on a live institutional product.
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
THE MISSION
METRIXX-ILLINI
is a dedicated development server — isolated from production — where the intern team builds, tests, and deploys independently. Code Name: MXXI Three core goals: ① Accelerate Phase 1 deliverables to Demo Day ② Cement each team member's authorship on a live product ③ Build a reusable architecture for Phase 2 (MRS, PREQUEL, VAULT Upload)
KEY MILESTONES
JUN 3
Server provisioned. Coolify + Cursor activated. New Claude API key live.
JUN 5
PostgreSQL schema migrated to ILLINI (Anna). Rocket.Chat provisioned.
JUN 7
Lambert delivers ETF prompt section to Aras.
JUN 8
Dimitris exposes 3 read-only API endpoints (Futures, Gamma Playbook, MIXX) with rate-limited dev key.
JUN 8
Typeform webhooks redirected to ILLINI (Anna).
JUN 12
DEMO DAY — Phase 1 MVP live.
JUN 13
Phase 2 begins: MRS MVP, PREQUEL Agent, VAULT Upload.

## Slide 3
MXXI — COMMAND STRUCTURE
Technical Lead holds full command authority over METRIXX-ILLINI. Dimitris owns production platform only.
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
JIM MARZANO
Founder & CEO · Strategic Direction
JOCELYN WU — TECHNICAL LEAD (ILLINI)
Full command authority over METRIXX-ILLINI · Code Authority · Python/C++/SQL · ICMRED 2024 publication
DIMITRIS — DEVOPS (PRODUCTION ONLY)
PRODUCTION server only · Must expose 3 read-only API endpoints by Jun 8 · No ILLINI architecture decisions
INTERN TEAM — REPORTS TO JOCELYN WU
LAMBERT HSU
Deputy Lead · MRS MVP · PREQUEL Agent
Phase 2 Primary
ARAS CHANG
Website Authority · Claude Code · Visual Ingestion Hub
Phase 1 Critical
ZILIN MAO
Analytics · Futures Prompts · MASSIVE Data Feed
Phase 1 Core
ANNA / CONG WANG
PostgreSQL Migration · Rocket.Chat · Typeform Webhooks
Phase 1 Infrastructure

## Slide 4
JOCELYN WU — TECHNICAL LEAD
Full-Stack Lead · Code Authority · Python/C++/SQL · ICMRED 2024
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
PHASE 1 DELIVERABLES (→ DEMO DAY JUN 12)
1. Claude API production integration — owns the API key, model selection, and token budget for ILLINI
2. WATOS™ scoring pipeline — five-factor /99 composite score appended to every Gamma Playbook report
3. Prompt Catalog architecture — encrypted, tiered prompt library schema and access control layer
4. PostgreSQL schema validation — confirm Anna's migration against production spec before Jun 6
5. VAULT™ file-naming standard enforcement — WATOS_{SUBSCRIBER_ID}_{UNDERLYING}_{STRATEGY_CODE}_{YYYYMMDD}_{SESSION}.ext
6. MCP schema ownership — delegates to team members, retains final authority
7. Phase 2 Kickoff Prep — Prompt Catalog mockup with Lambert (Claude design artifact, first Phase 2 week-one deliverable)
AUTHORITY
Code Authority — final say on all ILLINI commits API key owner for ILLINI workspace Jocelyn may block or revert any intern's production push Escalation path for Aras's Claude Code integration
PHASE 2 PREVIEW
VAULT Upload infrastructure (enabling dep for Lambert's MRS + PREQUEL) VAULT Upload endpoint live target: ~Jun 20 RPM Intelligence Layer — ICMRED 2024 publication framework

## Slide 5
LAMBERT HSU — DEPUTY LEAD
ETF Prompts · MIXX Regime Classification · MRS MVP · PREQUEL Agent (Phase 2)
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
PHASE 1 — PRE JUNE 12
1. ETF Prompt Section: 3 entries to Aras by Jun 7 (SPY regime, sector rotation, vol overlay)
2. MIXX ETF Regime Classification: co-author rules with Zilin, deliver spec to Jocelyn by Jun 8
DEPUTY LEAD ROLE
Lambert serves as Jocelyn's deputy and owns the Real Estate vertical in full. His classmate relationship with Jocelyn is a sprint accelerator — zero ramp-up on working trust. Lambert activates Phase 2 immediately June 13.
PHASE 2 — MRS MVP (June 13–30)
A1 Agent 1: Inbound Lead Capture (Typeform → PostgreSQL)
A2 Agent 2: Triage + Requirements Distribution (loan type classification)
A3 Agent 3: Document Ingestion (Make.com broker portal automation)
A4 Agent 4: Rate Engine — Optimal Blue API
A5 Agent 5: Disposition + Follow-Up → VAULT archive
PHASE 2 — PREQUEL AGENT (June 13–30)
→ Intake: Typeform → PostgreSQL principal/PASSPORT classification
→ Search: 3-source parallel (MRED, private markets, PROVIDER candidates)
→ Scoring: Claude at 66% match threshold
→ Output: Price-banded ranked results, up to 3 properties
→ Bridge: Optional MRS handoff on rate inquiry trigger

## Slide 6
ARAS CHANG — WEBSITE AUTHORITY & CLAUDE CODE LEAD
Visual Ingestion Hub · New Metrixx.ai Website · Prompt Engineering
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
NEW METRIXX.AI WEBSITE
Built from scratch using Claude Code. No clone of existing React/Node.js site. Claude-generated SVG graphics, new logo (3 directions), consistent design system. Aras owns all code and commits. Escalation path: Dimitris for infra only.
VISUAL INGESTION HUB
Native Claude API + Rocket.Chat pipeline (MAKE.com removed from ingestion scope). ClamAV 3-layer security scanning before any file processing. TradingView screenshots, PDFs, Excel sheets → structured intelligence output.
PROMPT CATALOG — ENGINEERING LAYER
Receives ETF prompts from Lambert by Jun 7. Owns catalog formatting, encryption tagging, and tiering schema. Works with Jocelyn on access control. Demo Day deliverable: encrypted Prompt Catalog with at minimum Futures, Gamma Playbook, and ETF sections populated.
CLAUDE CODE SUBSCRIPTION
Activate Claude Code Pro immediately. This is the primary build tool for the website and ingestion pipeline. Aras is the team's Claude Code authority — other interns route Claude Code questions through Aras, not Jocelyn (protect Jocelyn's capacity).

## Slide 7
ZILIN MAO — ANALYTICS SPECIALIST
Market Profile · Order Flow · Futures Prompts · MASSIVE Data Feed · BASIS SERVICE
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
PROMPT CATALOG — ANALYTICS COVERAGE (ZILIN'S DOMAIN)
CATEGORY | PROMPT SIGNALS | DATA SOURCE | OUTPUT TYPE | OWNER
Market Profile | TPO, VAH/VAL/POC, HVN/LVN, Initial Balance, Day Type Classification | Sierra Chart / MASSIVE | Structured JSON → MY DESK | Zilin
Order Flow | Volume Delta, Aggressor-Side Imbalance, Volume Velocity, Book Depth | MASSIVE (tick data) | Gamma Playbook overlay | Zilin
Micro Futures | MES, MNQ, MCL, MGC — position sizing, vol regimes, rollover triggers | CME via MASSIVE | Internal-use prompts (gated)* | Zilin + Lambert
MIXX Signals | PCA across top 25 CME futures, GEX layer, Level 2 volume composite | CME / SpotGamma equiv. | MIXX score /100 → subscriber feed | Zilin + Lambert
Commodity / BASIS | EIA, USDA AMS, CFTC COT, Baker Hughes rig count (–10 trigger) | Tier 1 Gov Sources | BASIS SENTIMENT alert → MY DESK | Zilin
Gamma Playbook | Dealer GEX, buy/sell pressure, options strategy scenarios + WATOS™ /99 | SpotGamma / internal | Strategy report + WATOS™ score | Jocelyn (WATOS) / Zilin (data)
MASSIVE Data Feed | GA June 2026 — tick data, snapshots, OHLC, Globex session status | Massive.io API | Replaces CME delayed endpoint | Zilin (validate by Jun 8)
* Micro Futures internal prompts gated — Jim must confirm production-readiness before release

## Slide 8
ANNA / CONG WANG — INFRASTRUCTURE MIGRATION
PostgreSQL Schema · Rocket.Chat Provisioning · Typeform Webhooks · Excel / XLAM
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
JUN 4–5
PostgreSQL Schema Migration
Dump schema-only from production (no live data). Restore to METRIXX-ILLINI DB. No subscriber records migrate — intern team works against a clean schema. Validate with Jocelyn before Jun 6.
JUN 5–6
Rocket.Chat Provisioning
Provision illini.metrixx.ai (or intern.metrixx.ai). Configure channels mirroring production MY DESK structure. Create intern user accounts. No subscriber data crosses.
JUN 6–7
Typeform Webhook Redirection
Redirect ILLINI-bound Typeform submissions (REGISTRY intake, PREQUEL form) to the ILLINI PostgreSQL instance. Production webhooks untouched. Confirm with Lambert before redirect is live.
ONGOING
Excel / XLAM Reporting
MRS Rate Deal File (6 sheets) and PREQUEL Property Deal File (7 sheets) — backend-push versioning via openpyxl. Cell ownership protection: backend-owned vs subscriber-owned ranges enforced.

## Slide 9
MXXI — SERVER ARCHITECTURE
Zero interface between PRODUCTION and METRIXX-ILLINI. Kill-switch on all intern access via separate API key.
METRIXX-ILLINI · MXXI · CONFIDENTIAL · DEMO DAY JUNE 12 2026
PRODUCTION
chat.metrixx.ai (MY DESK / Rocket.Chat)
Coolify / Linux — Dimitris owns
PostgreSQL — live subscriber data
Claude API — Production key (Dimitris)
Webflow — public marketing site
VAULT™ — subscriber archives
Gamma Playbook + WATOS™ — live
NO LINK
METRIXX-ILLINI (MXXI)
illini.metrixx.ai (Rocket.Chat — new)
Coolify / Linux — Jocelyn owns
PostgreSQL — schema-only clone, no live data
Claude API — ILLINI key (Jocelyn, $200/mo cap)
VAULT™ — schema stub, test records only
Claude Code — Aras leads, Cursor active
3 Read-only API endpoints from Dimitris (Jun 8)

## Slide 10
MXXI AUTHORSHIP COMPACT
Every team member's name ships with the product.
JOCELYN WU
Technical Lead & Code Authority. Your name anchors the Claude API integration and WATOS™ scoring pipeline. ICMRED 2024 authorship extends into Metrixx's RPM intelligence layer in Phase 2.
LAMBERT HSU
Deputy Lead. Your name is on the MRS MVP and PREQUEL Agent — the Bloomberg Terminal equivalent for mortgage and real estate intelligence. First institutional real estate AI product built on this architecture.
ARAS CHANG
Website & Claude Code Authority. The new metrixx.ai is your build. Every SVG, design system component, and Visual Ingestion Hub pipeline commit has your authorship.
ZILIN MAO
Analytics Specialist. Your prompt catalog section — Market Profile, Order Flow, Micro Futures, BASIS SERVICE, MASSIVE data feed — is the analytical engine every subscriber touches.
ANNA / CONG WANG
Infrastructure Foundation. The PostgreSQL migration, Rocket.Chat provisioning, and Typeform webhook architecture you build is what every other intern's work runs on. Invisible when it works. Irreplaceable.
Jim Marzano · Founder & CEO, Metrixx LLC · CBOT/CME Member · Founding Member GNMA Mortgage Futures · Original Bloomberg Data Contributor